## Sheet1
No | Point to evidence | Research question/task | Approx days to complete | Importance
1 | Increasingly large group showing signs of distress with housing costs | Check and present LIPR results | 2 | 5 | Time left to leaving | 20.75
2 | Increasingly large group showing signs of distress with housing costs | Show change over time | 2 | 4 | Minus handover time | 18.75
3 | Increasingly large group showing signs of distress with housing costs | Projection to 2021/2022 | 3 | 2 | Time on research report | 16.5
4 | Increasingly large group showing signs of distress with housing costs | TA/waiting lists | 0.5 | 3 | Time for launch story | 2.25
5 | Who are unable to access home ownership in the short term | Double check LIPR shared ownership results | 0.5 | 1
6 | And who are unlikely to access social housing due to short supply | How do the current numbers of people needing low rent homes and number of social/affordable rent homes compare? (turnover * stock?) | 2 | 5
7 | And who are unlikely to access social housing due to short supply | How is this likely to change in the future? (RtB? RtB extension?) | 1.5 | 2
8 | And who are unlikely to access social housing due to short supply | What is the shortfall in genuinely affordable social rented homes? | 3 | 3
9 | And who are unlikely to access social housing due to allocations | Who is currently receiving general needs social housing? | 2 | 4
10 | And who are unlikely to access social housing due to allocations | How does this compare to LIPR? | 1 | 4
11 | What level should rents be set at? | Conservative Living Rent/NLW update | 1 | 1
12 | How can new low rent product be funded? | Assuming ‘typical’ illustrative land costs, what is the subsidy needed to build? | 3 | 4
13 | How can new low rent product be funded? | Assuming lower land costs, what is the subsidy needed? | 1 | 3
22.5
16.5

## Sheet2
Base group | Stat needed | Survey years needed?
PRS with AHC under MIS | Number of households | 1
PRS with AHC under MIS | % of overall population | 1
PRS with AHC under MIS | % HRP employed | 2
PRS with AHC under MIS | median household income | 1
PRS with AHC under MIS | % children cf working age | 2
PRS with AHC under MIS | % single parent cf working age | 2
PRS with AHC under MIS | Region (number) | 1
PRS with AHC under MIS | Overlap with JAM group | 2?
PRS under 55 | No. can't afford Starter Homes | 1
PRS under 55 | No. can't afford Help to Buy | 1
PRS under 55 | No. can't afford Shared Ownership | 1
PRS under 55 + can't afford SO | Region (number) | 1
PRS under 55 + can't afford SO | Housing costs a burden
PRS under 55 + can't afford SO | No savings (%)
PRS under 55 + can't afford SO | Arrears on rent/other bills
PRS under 55 + can't afford SO | Ability to save £10 a month (number + %)
PRS under 55 + can afford SO | median savings
PRS under 55 + can afford SO | Arrears on rent/other bills (numbers + %)
PRS under 55 + can afford SO | Ability to save £10 a month
PRS under 55 + can't afford SO | % HRP employed (region) | 2
PRS under 55 + can't afford SO | % someone full-time (region) | 2
PRS under 65 + can't afford SO + non HB benefits < 20% | Total number
PRS under 65 + can't afford SO + non HB benefits < 20% | Median income (region) | 1 but investigate 2 years?
PRS under 65 + can't afford SO | Number cf to number of number of social/affordable rent homes(turnover * stock?)
PRS under 65 + can't afford SO + non HB benefits < 20% | Affordability of 80% market rent in each LA
PRS under 65 + can't afford SO + non HB benefits < 20% | Affordability of 30% of 30th percentile income in each LA
Modelling likely subsidy need